TERMS OF REFERENCE [TEMPLATE]

LANDSCALE ASSESSMENT TEAM

[Text highlighted in blue provides instructions and additional notes for the hiring organization.]

Important information

- Hiring organization: [name of organization]

- Website: [link to hiring organization’s website]

- Location: [city, country of hiring organization]

- Landscape title and location: [name and geographic location]

- Publication date: [Day/Month/Year of Terms of Reference publication]

- Application deadline: [Day/Month/Year]

About [organization name] and the landscape

[Provide a brief overview of the hiring organization, including its mission and key areas of work. Describe the landscape, its significance, and how LandScale is relevant in this context.]

About LandScale

LandScale offers a powerful platform designed to assess and communicate landscape sustainability performance. It provides landscape stakeholders with critical insights, supports informed decision-making, and enables the transparent sharing of credible impact stories. Companies, industry initiatives, NGOs, governments, donors, and financial institutions can use LandScale to evaluate the sustainability status and trends of landscapes with significant natural resource-based economies and supply chains.

The LandScale system—used to conduct this work—consists of the following key components:

- LandScale platform: The central hub for managing the entire assessment process. It allows assessment teams to assign tasks, input data, upload documents, access guidelines and training materials, request support, connect with other stakeholders, and engage with the LandScale community of practice. The platform also enables teams to publish landscape profiles and assessment reports, making findings accessible to a global audience.

- Assessment framework: Defines the pillars, goals, indicators, and metrics that shape the scope of an assessment.

- Validation mechanism: A structured review process conducted by the LandScale team (LandScale validation) and local experts (local review) to ensure the quality and credibility of assessments.

- Assessment guidelines: Detailed, step-by-step instructions for conducting a LandScale assessment, available on the LandScale platform.

- Claims policy: Outlines the types of claims that can be made based on assessment results and the appropriate process for communicating them.

Scope of work

LandScale’s assessment process consists of three steps.

[Customize this section to reflect the specific scope being sought. This includes an initial indication of the expected scope of indicators and metrics to be assessed, while allowing for further refinement through stakeholder engagement or selection during the process. Additionally, specify the consultant’s role, ranging from full project management and stakeholder coordination to more limited technical contributions.]

General requirements

- All inputs to the LandScale platform must be in English, using proper spelling and grammar. [Specify any other language requirements, e.g., a custom landscape report in the local language.]

- At the conclusion of each step, the assessment team must request validation by the LandScale team and work with LandScale to achieve satisfactory validation.

Step A: Landscape setup and boundary delineation

In this step, the assessment team undertakes the preparatory work necessary to conduct a LandScale assessment. This includes defining an appropriate assessment area based on the landscape’s context and characteristics. [Specify whether the consultant should conduct initial boundary delineation, refine an existing boundary, or not modify it at all.]

- Set up the landscape initiative.

- Define the landscape boundary.

- Conduct the adjacency analysis (optional).

- Document boundary limitations.

- Compile the landscape overview.

- Register assessment team members.

- Develop a stakeholder engagement plan.

- Compile documentation and submit the step for validation.

Step B: Indicator and metric selection

In this step, the assessment team selects the indicators and metrics used to assess landscape performance and trends. They may also begin identifying relevant data for each metric and analyzing their limitations, or can defer this to Step C.

- Select indicators and metrics to include in the assessment. [Clarify whether custom user-added indicators/metrics are needed or if only pre-defined LandScale indicators/metrics will be used.]

- Identify datasets and other data resources. [Specify any known data collection needs. Data collection may be required to achieve a ‘complete assessment’ status or to assess high-priority indicators for the landscape. The assessment team should work with the Assessment Owner to determine where data collection may be necessary.]

- Analyze data limitations, procure supplemental data where needed, manage any data gaps, and finalize data selection.

- Compile documentation and submit the step for validation.

Step C: Generate and publish results

In this step, the assessment team reviews and analyzes the selected data for each metric to generate results, undergoes a three-stage validation process—including a local review—and prepares for result publication.

- Process and analyze data to generate results for each metric.

- Set targets and milestones (optional).

- Identify and register local reviewers (if not done in an earlier step).

- Compile documentation and submit the step for the first LandScale review.

- Conduct the local review.

- Address feedback from the first LandScale review and the local review.

- Compile updated documentation and submit the step for the final validation.

- Publishing results on the relevant landscape profile on the LandScale platform.

- Generate a PDF report using the LandScale platform and submit it for validation (optional).

Activities within Step C may require:

- Integrating data from multiple sources.

- Classifying and coding data.

- Reviewing, validating, and editing data.

- Transforming data values or attributes.

- Imputing any missing data values, where possible.

- Deriving new variables and their values based on the source data.

- Calculating descriptive statistics (e.g., averages, distributions).

- Calculating quantitative measures of trends or rates.

- Assigning variable weights and calculating weighted averages or sums.

- Disaggregating data by appropriate variables and calculating metric values accordingly.

- Finalizing data files.

Activities required for Pillar 2, Goal 2.2 on human rights

| Relevant phase | Activities | Required outputs |
| --- | --- | --- |
| Phase 1: Initiate process and map stakeholders. This phase is linked to, and may be conducted in coordination with, Step A. | - Form the assessment team, ensuring alignment with LandScale guidelines and relevant expertise on human rights. - Conduct a desk-based study to develop a foundational understanding of human rights issues in the landscape. - Identify and map key stakeholders, and consult relevant groups and experts. | - Justification of the assessment team’s composition and capacity regarding human rights. - Stakeholder map. - Summary of stakeholder engagement documentation from this phase. - Key findings and conclusions from stakeholder consultations. |
| Phase 2: Analyze human rights issues and select indicators. This phase is linked to, and may be conducted in coordination with, Step B. | - Analyze insights from the stakeholder consultations conducted in Phase 1. - Assess the severity of human rights issues in the landscape and determine which indicators are applicable. | - Selection of applicable indicators. - Summary of stakeholder engagement documentation from this phase. |
| Phase 3: Analyze enabling conditions and design metrics. This phase is linked to, and may be conducted in coordination with, Step B. | - Identify the root causes of actual and potential adverse human rights impacts and determine the enabling conditions needed to address them at the landscape level. - Design metrics to assess the most critical enabling conditions that support the prevention, mitigation, and remediation of human rights issues. Ensure these metrics effectively measure the status of, or progress towards, achieving these conditions. | - List of identified enabling conditions for each applicable indicator. - List of proposed metrics, including their desired status or outcomes. - Summary stakeholder engagement documentation from this phase. |
| Phase 4: Evaluate metrics and report results. This phase is linked to, and may be conducted in coordination with, Step C. | - Assess the selected metrics and ensure the results are validated. - Share results with key stakeholders, especially rights holders. | - Assessment results for each metric. - Summary stakeholder engagement documentation from this phase. |

Milestones and timeline

| Milestone | Activities | Timeline |
| --- | --- | --- |
| Initiation meeting | - [Specify key activities.] | Day/Month/Year - Day/Month/Year |
| Detailed work plan finalized | - [Specify key activities.] | Day/Month/Year - Day/Month/Year |
| Step A completed | - [Specify key activities.] | Day/Month/Year - Day/Month/Year |
| Step B completed | - [Specify key activities.] | Day/Month/Year - Day/Month/Year |
| Step C completed | - [Specify key activities.] | Day/Month/Year - Day/Month/Year |

Budget

[Name of organization] has allocated a budget in the range of [XX-XX] for this consultancy.

Payment schedule

Payments will be made upon successful LandScale validation of each step.

| Step | Deliverables | Payment (% of total) |
| --- | --- | --- |
| Step A | - General landscape information (landscape name, assessment name, organizations acting as stakeholders, objectives of the assessment). - Landscape boundary in .shp or .kml format. - Size of the landscape boundary (in square kilometers or hectares). - A brief rationale for the proposed landscape boundary. - Limitations of the selected boundary. - Adjacency analysis documentation (if completed), including: - Findings related to the three aspects of adjacency described in the boundary limitations and adjacency analysis guidelines. - Conclusion of the analysis and a summary of any resulting adjustments made to the boundary. - Assessment team composition, including: - Registration of all team members on the platform. - A brief description of each member’s qualifications relevant to the assessment scope, supported by evidence such as CVs, resumes, courses certifications, or other suitable documentation. - Stakeholder engagement plan. | [Percentage of total payment] |
| Step B | - Identification of all core and additional indicators to be included in the assessment. - Appropriate justification for the deselection or deferral of any core indicators. - Description of any user-added indicators and a rationale for their inclusion. - Documentation of the process used to determine and justify the applicability of additional indicators, including any stakeholder consultation or desk-based research (optional). - If any human rights indicators within Goal 2.2 are included in the assessment scope, documentation demonstrating how these were selected in accordance with the Human Rights Assessment Guidelines. Optionally, this documentation may also be submitted for any user-added human rights-related indicators. - Identification of all essential and complementary metrics to be included for each selected indicator. - Description of any user-added metrics and a rationale for their inclusion, including their relevance to the indicator. - If the essential metrics that constitute a core indicator are modified—such as by deselecting LandScale-defined essential metrics or designating user-added metrics as essential—appropriate justification for these changes must be provided. While optional for additional indicators, providing justification is recommended. - Identification of all selected data resources (may be submitted during Step B or C validation). - Documentation of the outcome of the data limitations analysis for each data resource (may be submitted during Step B or C validation). - Documentation related to any primary data collection, in accordance with the guidelines. This documentation should be added within the dataset description and metadata fields that are available in the platform for each dataset (may be submitted during Step B or C validation). - Identification of metrics and indicators designated as data-deficient or otherwise deferred, along with a statement of the reason for these decisions (may be submitted during Step B or C validation). | [Percentage of total payment] |
| Step C | - Documentation of the local review process, forms of engagement with local reviewers, and Conflict of Interest Declarations for all the local reviewers, in accordance with the local review guidelines. - Documentation of how the assessment team resolved each issue raised through the local review or the first LandScale review, following the respective resolution options detailed in the guidelines. - Final assessment results—including associated limitation statements and documentation—reflecting any of the previously detailed changes. - Optional landscape report with data visualizations of assessment results. | [Percentage of total payment] |

Qualifications

[If other specialists (e.g., from organizations that are part of the Landscape Initiative) will be committing time to support the assessment team hired through this Terms of Reference, adjust the qualifications as necessary. This may involve removing any qualifications already covered by those specialists or changing their status from required to preferred, where appropriate. In addition to the Assessment Owner, the team may also require an Assessment Lead to oversee the day-to-day tasks on the LandScale platform.]

Subject matter expertise

The assessment team must have technical expertise across all sustainability themes within the assessment scope. This includes interdisciplinary knowledge in areas such as land use, natural resource management, commodity production, social development, and governance, as well as sector-specific expertise in agriculture or forestry if these are relevant to the landscape.

The team's expertise must cover all pillars of the LandScale assessment framework. Below is a summary of the areas where expertise is needed. Some areas marked '(optional)' indicate expertise that may only be required if those specific indicators are included in the assessment.

Pillar 1: Ecosystems

- Natural ecosystem protection, conversion, and degradation.

- Biodiversity habitat protection, conversion, degradation, and restoration.

- Restoration of converted and degraded ecosystems (optional).

- Connectivity and fragmentation of natural ecosystems (optional).

- Water resources measurement (optional).

- Greenhouse gas emissions (sources) and carbon sequestration (sinks) associated with agriculture, forestry, and other land use activities (optional).

- Ecosystem services measurement (optional).

Pillar 2: Human well-being

Due to the sensitive nature of human rights issues addressed by the LandScale framework, the assessment team must meet specific qualifications for assessing human rights indicators. This includes expertise related to the human rights issues covered in the LandScale framework (child labor, women's rights, Indigenous peoples' and other marginalized groups' rights, forced labor, and workers' rights).

At a minimum, the team must include an expert who meets the following qualifications to ensure that the human rights indicators are assessed in a rigorous and objective manner:

- Proficiency in the local language(s) of the landscape.

- Commitment to objective and inclusive assessments, including a willingness to engage with marginalized or vulnerable groups separately as needed.

- At least 3 years of experience in human rights issues and impact assessments.

- Strong understanding of key human rights issues affecting local people and communities. Experience conducting surveys, interviews, focus groups, and other types of engagements with workers, households, and local communities.

- Familiarity with the local culture, context, and politics.

Additional areas of expertise needed within this pillar include:

- Multidimensional poverty assessments, covering education, sanitation, health, nutrition, etc.

- Human rights impact assessments (child labor, forced labor, workers’ rights) (optional).

Pillar 3: Governance

- Land and resource tenure.

- Land and resource conflicts.

- Transparency, participation, inclusion, and coordination in land-use policy, planning, and management.

- Illegality and corruption related to land and resources (optional).

Pillar 4: Production

- Productivity of agricultural (crop and livestock), agroforestry, and tree production systems in the landscape (optional).

- Efficiency of input use in agricultural, agroforestry, and tree production systems in the landscape (optional).

- Adoption of sustainable land management and waste management practices in agricultural and forest plantation operations in the landscape (optional).

- Expertise in other natural resource-based production sectors (optional).

Technical expertise

Data and analysis

- Expertise in social and environmental data collection and analysis.

- Ability to identify data sources, assess data quality, and calculate metrics from primary and secondary data.

GIS and data manipulation and management

Spatial information is a key component of a LandScale assessment. For this reason, the team should include one or more people experienced in the following:

- Proficiency in spatial data collection, management, and analysis using GIS software.

- Mapping skills to complete the landscape overview.

Other preferred qualifications

Writing skills

- Strong writing and editing skills in English to support the development of the landscape profile and final assessment report.

- Ability to translate findings into locally relevant languages and culturally appropriate formats for relevant audiences, as needed.

Data visualization skills

- Ability to create visualizations (e.g., maps, charts, infographics) to enhance the landscape profile and assessment report.

- Inclusion of team members with graphic design and production skills is recommended.

Criteria for selection

The following criteria will be prioritized by [name of hiring organization] when evaluating proposals:

- Knowledge and familiarity with the landscape.

- Location of the team relative to the landscape (e.g., within a one-day travel radius, within the same time zone).

- Team composition and relevant experience in relation to the scope of the assessment.

- Proficiency in X language.

- Value relative to cost and scope.

Although these preparatory tasks occur at the beginning of the process, the assessment team is encouraged to revisit and refine the analyses as needed.

Before initiating the desk-based study, the assessment team should already have narrowed down the scope of economic activities that the human rights assessment will cover.